## Raw Data
Project_ID | Project_Name | Phase | Contractor | Material_Cost_EUR | Labor_Cost_EUR | Planned_Start | Actual_Start | Planned_End | Actual_End | Budget_EUR | Status | Notes
P1000 | Mitte Office Tower | foundation | STRABAG SE | 58753.76 | 76754.98 | 16.01.2023 | 2023-02-01 | 31/03/2023 | 03/26/2023 | 124256.53 | On Hold
P1025 | Friedrichshain Loft | Structure | Max Bögl | 142965.08 | 52249.31 | 23.03.2023 | 2023-03-28 | 06/05/2023 | 04/26/2023 | 203735.54 | ON HOLD
P1010 | Prenzlauer Berg Retail | Finishing | Bilfinger SE | 137994.94 | 124048.4 | 25.05.2023 | 2023-06-12 | 11/07/2023 | 08/04/2023 | 296824.16 | delayed
P1005 | Kreuzberg Residential | Structure | Züblin AG | 179563.34 | 65616.2 | 26.03.2023 | 2023-04-10 | 09/05/2023 | 06/06/2023 | 228039.86 | COMPLETED | Check invoice
P1007 | Kreuzberg Residential | mep | Goldbeck GmbH | 73166.01 | 185233.14 | 19.07.2023 | 2023-07-20 | 28/09/2023 | 10/13/2023 | 263606.93 | on hold
P1014 | Charlottenburg Hotel | Finishing | Bilfinger SE | 107794.44 | 119704.54 | 18.05.2023 | 2023-05-30 | 09/07/2023 | 07/18/2023 | 234773.98 | ON HOLD | Material delay
P1003 | Mitte Office Tower | Mep | Hochtief AG | 346623.03 | 132633.43 | 21.07.2023 | 2023-08-02 | 06/09/2023 | 09/20/2023 | 523414.42 | in progress | Material delay
P1021 | Spandau Logistics Hub | Structure | Ed. Züblin | 365855 | 57988.31 | 22.03.2023 | 2023-03-25 | 30/05/2023 | 06/07/2023 | 360540.88 | ON HOLD | TBC
P1031 | Wedding School Extension | MEP | Goldbeck GmbH | 177628.03 | 188624.96 | 14.07.2023 | 2023-07-20 | 05/09/2023 | 09/10/2023 | 418135.98 | IN PROGRESS | N/A
P1038 | Lichtenberg Warehouse | FINISHING | Porr GmbH | 159870.48 | 174162.6 | 19.05.2023 | 2023-05-30 | 17/07/2023 | 08/02/2023 | 356054.64 | DELAYED | Pending approval
P1000 | Mitte Office Tower | foundation | STRABAG SE | 58753.76 | 76754.98 | 16.01.2023 | 2023-02-01 | 31/03/2023 | 03/26/2023 | 124256.53 | On Hold
P1016 | Neukölln Mixed-Use | FOUNDATION | STRABAG SE | 297744.33 | 40008.54 | 15.01.2023 | 2023-01-20 | 28/02/2023 | 03/22/2023 | 293919.34 | COMPLETED | n/a
P1013 | Charlottenburg Hotel | structure | Goldbeck GmbH | 133808.31 | 70948.17 | 17.03.2023 | 2023-03-14 | 27/05/2023 | 05/21/2023 | 208894.01 | COMPLETED | n/a
P1011 | Prenzlauer Berg Retail | Mep | Goldbeck GmbH | 202167.84 | 107133.03 | 18.07.2023 | 2023-07-29 | 07/09/2023 | 09/29/2023 | 351410.57 | in progress | TBC
P1002 | Mitte Office Tower | finishing | Bauer GmbH | 315582.58 | 57142.08 | 19.05.2023 | 2023-05-18 | 11/07/2023 | 07/22/2023 | 364071.6 | in progress
P1036 | Lichtenberg Warehouse | FOUNDATION | Bauer GmbH | 87940.89 | 103875.84 | 20.01.2023 | 2023-01-28 | 08/04/2023 | 04/30/2023 | 204968.36 | IN PROGRESS | Check invoice
P1006 | Kreuzberg Residential | finishing | Züblin AG | 211791.07 | 75891.13 | 23.05.2023 | 2023-05-25 | 22/07/2023 | 07/15/2023 | 324395.44 | completed | N/A
P1023 | Spandau Logistics Hub | Mep | Bilfinger SE | 371785.5 | 120291.44 | 22.07.2023 | 2023-07-19 | 11/09/2023 | 09/05/2023 | 426662.14 | In Progress | N/A
P1009 | Prenzlauer Berg Retail | STRUCTURE | STRABAG SE | 314523.76 | 176387.49 | 18.03.2023 | 2023-04-07 | 24/05/2023 | 06/21/2023 | 439784.02 | in progress | n/a
P1039 | Lichtenberg Warehouse | MEP | Bilfinger SE | 94550.73 | 101475.88 | 24.07.2023 | 2023-08-11 | 13/09/2023 | 10/12/2023 | 221923.51 | DELAYED
P1035 | Steglitz Medical Centre | mep | Hochtief AG | 274518.61 | 97945.33 | 22.07.2023 | 2023-07-27 | 01/09/2023 | 08/29/2023 | 426227.21 | DELAYED | Pending approval
P1034 | Steglitz Medical Centre | FINISHING | Implenia DE | 172380.45 | 169491.18 | 18.05.2023 | 2023-05-13 | 09/07/2023 | 07/24/2023 | 379955.07 | Delayed | Pending approval
P1015 | Charlottenburg Hotel | Mep | Implenia DE | 364864.93 | 106752.64 | 15.07.2023 | 2023-07-20 | 25/08/2023 | 09/21/2023 | 435949.93 | Completed
P1008 | Prenzlauer Berg Retail | foundation | Max Bögl | 310746.14 | 121626.14 | 21.01.2023 | 2023-02-03 | 27/03/2023 | 04/09/2023 | 464412.86 | COMPLETED | n/a
P1001 | Mitte Office Tower | STRUCTURE | Max Bögl | 131431.31 | 132343.18 | 26.03.2023 | 2023-04-12 | 08/06/2023 | 06/24/2023 | 268620.96 | COMPLETED | Pending approval
P1020 | Spandau Logistics Hub | FOUNDATION | Bauer GmbH | 278250.71 | 121899.95 | 16.01.2023 | 2023-02-04 | 12/03/2023 | 03/12/2023 | 341899.67 | on hold | Check invoice
P1004 | Kreuzberg Residential | FOUNDATION | Porr GmbH | 117301.01 | 41824.38 | 19.01.2023 | 2023-01-16 | 14/03/2023 | 03/10/2023 | 166823.72 | on hold | Material delay
P1022 | Spandau Logistics Hub | finishing | Implenia DE | 104178.89 | 80440.33 | 24.05.2023 | 2023-06-11 | 06/08/2023 | 07/30/2023 | 210579.05 | Delayed | n/a
P1030 | Wedding School Extension | FINISHING | Bilfinger SE | 296983.61 | 125354.17 | 17.05.2023 | 2023-05-29 | 28/06/2023 | 07/11/2023 | 373161.68 | Completed
P1032 | Steglitz Medical Centre | foundation | Porr GmbH | 312317.16 | 187379.85 | 17.01.2023 | 2023-02-06 | 09/03/2023 | 03/25/2023 | 460231.54 | IN PROGRESS | Material delay
P1024 | Friedrichshain Loft | FOUNDATION | STRABAG SE | 379558.64 | 126844.82 | 15.01.2023 | 2023-01-29 | 01/03/2023 | 03/17/2023 | 518392.93 | Delayed | Material delay
P1029 | Wedding School Extension | structure | Bauer GmbH | 82304.46 | 102007.88 | 16.03.2023 | 2023-03-21 | 03/05/2023 | 06/02/2023 | 171964.16 | DELAYED | n/a
P1037 | Lichtenberg Warehouse | structure | Goldbeck GmbH | 65535.29 | 104129.78 | 24.03.2023 | 2023-04-09 | 15/05/2023 | 05/28/2023 | 170679.01 | ON HOLD | Material delay
P1033 | Steglitz Medical Centre | STRUCTURE | Ed. Züblin | 330782.3 | 176890.88 | 20.03.2023 | 2023-03-20 | 05/05/2023 | 05/19/2023 | 555000.91 | In Progress | Check invoice
P1027 | Friedrichshain Loft | mep | Goldbeck GmbH | 264087.22 | 197829.62 | 14.07.2023 | 2023-07-30 | 27/09/2023 | 10/06/2023 | 483254.12 | in progress
P1028 | Wedding School Extension | Foundation | STRABAG SE | 309845.84 | 56426.14 | 18.01.2023 | 2023-02-04 | 20/03/2023 | 03/23/2023 | 342291.01 | delayed | Pending approval
P1019 | Neukölln Mixed-Use | MEP | Max Bögl | 117056.53 | 121168.58 | 16.07.2023 | 2023-07-19 | 23/09/2023 | 09/28/2023 | 212509.83 | IN PROGRESS
P1026 | Friedrichshain Loft | finishing | STRABAG SE | 238172.04 | 116000.4 | 20.05.2023 | 2023-05-17 | 14/07/2023 | 07/27/2023 | 315120.31 | delayed | TBC
P1012 | Charlottenburg Hotel | foundation | Porr GmbH | 119618.89 | 93565.35 | 23.01.2023 | 2023-01-18 | 11/04/2023 | 04/21/2023 | 191538.52 | On Hold | Material delay
P1017 | Neukölln Mixed-Use | structure | Max Bögl | 238731.88 | 152969.94 | 25.03.2023 | 2023-04-04 | 19/05/2023 | 06/08/2023 | 436635.86 | On Hold
P1018 | Neukölln Mixed-Use | Finishing | Ed. Züblin | 174004.15 | 99887.39 | 15.05.2023 | 2023-05-31 | 30/06/2023 | 06/23/2023 | 303787.08 | on hold

## 2_Contractor_Rates
Contractor_Name | Daily_Rate_EUR | Overhead_% | Specialization | Risk_Rating | Region
Bauer GmbH | 1850 | 12% | Geotechnical | Low | Berlin
STRABAG SE | 2200 | 15% | General Civil | Low | National
Züblin AG | 2100 | 14% | Structural | Low | National
Max Bögl | 1950 | 13% | Precast | Medium | Bavaria
Goldbeck GmbH | 1800 | 11% | Commercial | Low | National
Hochtief AG | 2400 | 16% | Large Scale | Low | International
Ed. Züblin | 2050 | 14% | Structural | Medium | National
Implenia DE | 1900 | 12% | Mixed-Use | Low | National
Bilfinger SE | 2150 | 15% | Industrial | Medium | National
Porr GmbH | 1750 | 11% | Residential | Low | Berlin

## 3_Cleaned_Data
Project _ID | Project_Name | Phase | Contractor | Material_Cost_EUR | Labour_Cost_EUR | Planned _Start | Actual_start | Planned_End | Actual_End | Budget_EUR | Actual_Cost_EUR | Variance_EUR | Variance_% | Status | Contractor_Daily_Rate | Overhead_% | Days_Delay
P1000 | Mitte Office Tower | Foundation | STRABAG SE | 58753.76 | 76754.98 | 16.01.2023 | 2023-02-01 | 2023-03-31 | 2023-03-26 | 124256.53 | 135508.74 | 11252.21 | 9.056% | On Hold | 2200 | 15% | -5
P1025 | Friedrichshain Loft | Structure | Max Bögl | 142965.08 | 52249.31 | 23.03.2023 | 2023-03-28 | 2023-05-06 | 2023-04-26 | 203735.54 | 195214.39 | -8521.15 | -4.182% | On Hold | 1950 | 13% | -10
P1010 | Prenzlauer Berg Retail | Finishing | Bilfinger SE | 137994.94 | 124048.4 | 25.05.2023 | 2023-06-12 | 2023-07-11 | 2023-08-04 | 296824.16 | 262043.34 | -34780.82 | -11.72% | Delayed | 2150 | 15% | 24
P1005 | Kreuzberg Residential | Structure | Züblin AG | 179563.34 | 65616.2 | 26.03.2023 | 2023-04-10 | 2023-05-09 | 2023-06-06 | 228039.86 | 245179.54 | 17139.68 | 7.516% | Completed | 2100 | 14% | 28
P1007 | Kreuzberg Residential | Mep | Goldbeck GmbH | 73166.01 | 185233.14 | 19.07.2023 | 2023-07-20 | 2023-09-28 | 2023-10-13 | 263606.93 | 258399.15 | -5207.78 | -1.976% | On Hold | 1800 | 11% | 15
P1014 | Charlottenburg Hotel | Finishing | Bilfinger SE | 107794.44 | 119704.54 | 18.05.2023 | 2023-05-30 | 2023-07-09 | 2023-07-18 | 234773.98 | 227498.98 | -7275 | -3.099% | On Hold | 2150 | 15% | 9
P1003 | Mitte Office Tower | Mep | Hochtief AG | 346623.03 | 132633.43 | 21.07.2023 | 2023-08-02 | 2023-09-06 | 2023-09-20 | 523414.42 | 479256.46 | -44157.96 | -8.437% | In Progress | 2400 | 16% | 14
P1021 | Spandau Logistics Hub | Structure | Ed. Züblin | 365855 | 57988.31 | 22.03.2023 | 2023-03-25 | 2023-05-30 | 2023-06-07 | 360540.88 | 423843.31 | 63302.43 | 17.56% | On Hold | 2050 | 14% | 8
P1031 | Wedding School Extension | Mep | Goldbeck GmbH | 177628.03 | 188624.96 | 14.07.2023 | 2023-07-20 | 2023-09-05 | 2023-09-10 | 418135.98 | 366252.99 | -51882.99 | -12.41% | In Progress | 1800 | 11% | 5
P1038 | Lichtenberg Warehouse | Finishing | Porr GmbH | 159870.48 | 174162.6 | 19.05.2023 | 2023-05-30 | 2023-07-17 | 2023-08-02 | 356054.64 | 334033.08 | -22021.56 | -6.185% | Delayed | 1750 | 11% | 16
P1016 | Neukölln Mixed-Use | Foundation | STRABAG SE | 297744.33 | 40008.54 | 15.01.2023 | 2023-01-20 | 2023-02-28 | 2023-03-22 | 293919.34 | 337752.87 | 43833.53 | 14.91% | Completed | 2200 | 15% | 22
P1013 | Charlottenburg Hotel | Structure | Goldbeck GmbH | 133808.31 | 70948.17 | 17.03.2023 | 2023-03-14 | 2023-05-27 | 2023-05-21 | 208894.01 | 204756.48 | -4137.53 | -1.981% | Completed | 1800 | 11% | -6
P1011 | Prenzlauer Berg Retail | Mep | Goldbeck GmbH | 202167.84 | 107133.03 | 18.07.2023 | 2023-07-29 | 2023-09-07 | 2023-09-29 | 351410.57 | 309300.87 | -42109.7 | -11.98% | In Progress | 1800 | 11% | 22
P1002 | Mitte Office Tower | Finishing | Bauer GmbH | 315582.58 | 57142.08 | 19.05.2023 | 2023-05-18 | 2023-07-11 | 2023-07-22 | 364071.6 | 372724.66 | 8653.06 | 2.377% | In Progress | 1850 | 12% | 11
P1036 | Lichtenberg Warehouse | Foundation | Bauer GmbH | 87940.89 | 103875.84 | 20.01.2023 | 2023-01-28 | 2023-04-08 | 2023-04-30 | 204968.36 | 191816.73 | -13151.63 | -6.416% | In Progress | 1850 | 12% | 22
P1006 | Kreuzberg Residential | Finishing | Züblin AG | 211791.07 | 75891.13 | 23.05.2023 | 2023-05-25 | 2023-07-22 | 2023-07-15 | 324395.44 | 287682.2 | -36713.24 | -11.32% | Completed | 2100 | 14% | -7
P1023 | Spandau Logistics Hub | Mep | Bilfinger SE | 371785.5 | 120291.44 | 22.07.2023 | 2023-07-19 | 2023-09-11 | 2023-09-05 | 426662.14 | 492076.94 | 65414.8 | 15.33% | In Progress | 2150 | 15% | -6
P1009 | Prenzlauer Berg Retail | Structure | STRABAG SE | 314523.76 | 176387.49 | 18.03.2023 | 2023-04-07 | 2023-05-24 | 2023-06-21 | 439784.02 | 490911.25 | 51127.23 | 11.63% | In Progress | 2200 | 15% | 28
P1039 | Lichtenberg Warehouse | Mep | Bilfinger SE | 94550.73 | 101475.88 | 24.07.2023 | 2023-08-11 | 2023-09-13 | 2023-10-12 | 221923.51 | 196026.61 | -25896.9 | -11.67% | Delayed | 2150 | 15% | 29
P1035 | Steglitz Medical Centre | Mep | Hochtief AG | 274518.61 | 97945.33 | 22.07.2023 | 2023-07-27 | 2023-09-01 | 2023-08-29 | 426227.21 | 372463.94 | -53763.27 | -12.61% | Delayed | 2400 | 16% | -3
P1034 | Steglitz Medical Centre | Finishing | Implenia DE | 172380.45 | 169491.18 | 18.05.2023 | 2023-05-13 | 2023-07-09 | 2023-07-24 | 379955.07 | 341871.63 | -38083.44 | -10.02% | Delayed | 1900 | 12% | 15
P1015 | Charlottenburg Hotel | Mep | Implenia DE | 364864.93 | 106752.64 | 15.07.2023 | 2023-07-20 | 2023-08-25 | 2023-09-21 | 435949.93 | 471617.57 | 35667.64 | 8.182% | Completed | 1900 | 12% | 27
P1008 | Prenzlauer Berg Retail | Foundation | Max Bögl | 310746.14 | 121626.14 | 21.01.2023 | 2023-02-03 | 2023-03-27 | 2023-04-09 | 464412.86 | 432372.28 | -32040.58 | -6.899% | Completed | 1950 | 13% | 13
P1001 | Mitte Office Tower | Structure | Max Bögl | 131431.31 | 132343.18 | 26.03.2023 | 2023-04-12 | 2023-06-08 | 2023-06-24 | 268620.96 | 263774.49 | -4846.47 | -1.804% | Completed | 1950 | 13% | 16
P1020 | Spandau Logistics Hub | Foundation | Bauer GmbH | 278250.71 | 121899.95 | 16.01.2023 | 2023-02-04 | 2023-03-12 | 2023-03-12 | 341899.67 | 400150.66 | 58250.99 | 17.04% | On Hold | 1850 | 12% | 0
P1004 | Kreuzberg Residential | Foundation | Porr GmbH | 117301.01 | 41824.38 | 19.01.2023 | 2023-01-16 | 2023-03-14 | 2023-03-10 | 166823.72 | 159125.39 | -7698.33 | -4.615% | On Hold | 1750 | 11% | -4
P1022 | Spandau Logistics Hub | Finishing | Implenia DE | 104178.89 | 80440.33 | 24.05.2023 | 2023-06-11 | 2023-08-06 | 2023-07-30 | 210579.05 | 184619.22 | -25959.83 | -12.33% | Delayed | 1900 | 12% | -7
P1030 | Wedding School Extension | Finishing | Bilfinger SE | 296983.61 | 125354.17 | 17.05.2023 | 2023-05-29 | 2023-06-28 | 2023-07-11 | 373161.68 | 422337.78 | 49176.1 | 13.18% | Completed | 2150 | 15% | 13
P1032 | Steglitz Medical Centre | Foundation | Porr GmbH | 312317.16 | 187379.85 | 17.01.2023 | 2023-02-06 | 2023-03-09 | 2023-03-25 | 460231.54 | 499697.01 | 39465.47 | 8.575% | In Progress | 1750 | 11% | 16
P1024 | Friedrichshain Loft | Foundation | STRABAG SE | 379558.64 | 126844.82 | 15.01.2023 | 2023-01-29 | 2023-03-01 | 2023-03-17 | 518392.93 | 506403.46 | -11989.47 | -2.313% | Delayed | 2200 | 15% | 16
P1029 | Wedding School Extension | Structure | Bauer GmbH | 82304.46 | 102007.88 | 16.03.2023 | 2023-03-21 | 2023-05-03 | 2023-06-02 | 171964.16 | 184312.34 | 12348.18 | 7.181% | Delayed | 1850 | 12% | 30
P1037 | Lichtenberg Warehouse | Structure | Goldbeck GmbH | 65535.29 | 104129.78 | 24.03.2023 | 2023-04-09 | 2023-05-15 | 2023-05-28 | 170679.01 | 169665.07 | -1013.94 | -0.5941% | On Hold | 1800 | 11% | 13
P1033 | Steglitz Medical Centre | Structure | Ed. Züblin | 330782.3 | 176890.88 | 20.03.2023 | 2023-03-20 | 2023-05-05 | 2023-05-19 | 555000.91 | 507673.18 | -47327.73 | -8.528% | In Progress | 2050 | 14% | 14
P1027 | Friedrichshain Loft | Mep | Goldbeck GmbH | 264087.22 | 197829.62 | 14.07.2023 | 2023-07-30 | 2023-09-27 | 2023-10-06 | 483254.12 | 461916.84 | -21337.28 | -4.415% | In Progress | 1800 | 11% | 9
P1028 | Wedding School Extension | Foundation | STRABAG SE | 309845.84 | 56426.14 | 18.01.2023 | 2023-02-04 | 2023-03-20 | 2023-03-23 | 342291.01 | 366271.98 | 23980.97 | 7.006% | Delayed | 2200 | 15% | 3
P1019 | Neukölln Mixed-Use | Foundation | Max Bögl | 117056.53 | 121168.58 | 16.07.2023 | 2023-07-19 | 2023-09-23 | 2023-09-28 | 212509.83 | 238225.11 | 25715.28 | 12.1% | In Progress | 1950 | 13% | 5
P1026 | Friedrichshain Loft | Finishing | STRABAG SE | 238172.04 | 116000.4 | 20.05.2023 | 2023-05-17 | 2023-07-14 | 2023-07-27 | 315120.31 | 354172.44 | 39052.13 | 12.39% | Delayed | 2200 | 15% | 13
P1012 | Charlottenburg Hotel | Foundation | Porr GmbH | 119618.89 | 93565.35 | 23.01.2023 | 2023-01-18 | 2023-04-11 | 2023-04-21 | 191538.52 | 213184.24 | 21645.72 | 11.3% | On Hold | 1750 | 11% | 10
P1017 | Neukölln Mixed-Use | Structure | Max Bögl | 238731.88 | 152969.94 | 25.03.2023 | 2023-04-04 | 2023-05-19 | 2023-06-08 | 436635.86 | 391701.82 | -44934.04 | -10.29% | On Hold | 1950 | 13% | 20
P1018 | Neukölln Mixed-Use | Finishing | Ed. Züblin | 174004.15 | 99887.39 | 15.05.2023 | 2023-05-31 | 2023-06-30 | 2023-06-23 | 303787.08 | 273891.54 | -29895.54 | -9.841% | On Hold | 2050 | 14% | -7

## 4_Pivot_Analysis
phase | Budget | Actual Cost | Variance | Variance % | Status
Foundation | 3321244.31 | 3480508.47 | 159264.16 | 0.047953 | Watch
Structure | 3043895.21 | 3077031.87 | 33136.66 | 0.010886 | Watch
Finishing | 3158723.01 | 3060874.87 | -97848.14 | -0.030977 | On Track
Mep | 3550584.81 | 3407311.37 | -143273.44 | -0.040352 | On Track
Total | 13074447.34 | 13025726.58 | -48720.76 | -0.3726% | On Track
Project Name | Foundation | Structure | Finishing | Mep | Grand Total
Mitte Office Tower | 135508.74 | 263774.49 | 372724.66 | 479256.46 | 1251264.35
Kreuzberg Residential | 159125.39 | 245179.54 | 287682.2 | 258399.15 | 950386.28
Prenzlauer Berg Retail | 432372.28 | 490911.25 | 262043.34 | 309300.87 | 1494627.74
Charlottenburg Hotel | 213184.24 | 204756.48 | 227498.98 | 471617.57 | 1117057.27
Neukölln Mixed-Use | 575977.98 | 391701.82 | 273891.54 | 0 | 1241571.34
Spandau Logistics Hub | 400150.66 | 423843.31 | 184619.22 | 492076.94 | 1500690.13
Friedrichshain Loft | 506403.46 | 195214.39 | 354172.44 | 461916.84 | 1517707.13
Wedding School Extension | 366271.98 | 184312.34 | 422337.78 | 366252.99 | 1339175.09
Steglitz Medical Centre | 499697.01 | 507673.18 | 341871.63 | 372463.94 | 1721705.76
Lichtenberg Warehouse | 191816.73 | 169665.07 | 334033.08 | 196026.61 | 891541.49
TOTAL |  |  |  |  | 13025726.58
Contractor | Total Budget | Total Actual | Variance | Variance %
Bauer GmbH | 1082903.79 | 1149004.39 | 66100.6 | 6.104%
STRABAG SE | 2033764.14 | 2191020.74 | 157256.6 | 7.732%
Züblin AG | 552435.3 | 532861.74 | -19573.56 | -3.543%
Max Bögl | 1585915.05 | 1521288.09 | -64626.96 | -4.075%
Goldbeck GmbH | 1895980.62 | 1770291.4 | -125689.22 | -6.629%
Hochtief AG | 949641.63 | 851720.4 | -97921.23 | -10.31%
Ed. Züblin | 1219328.87 | 1205408.03 | -13920.84 | -1.142%
Implenia DE | 1026484.05 | 998108.42 | -28375.63 | -2.764%
Bilfinger SE | 1553345.47 | 1599983.65 | 46638.18 | 3.002%
Porr GmbH | 1174648.42 | 1206039.72 | 31391.3 | 2.672%
Total | 13074447.34 | 13025726.58 | -48720.76 | -0.3726%

## 5_Budget_vs_Actual
Project Name | Phase | Contractor | Budget | Actual Cost | Variance | Variance % | RAG Status
Mitte Office Tower | Foundation | STRABAG SE | 124256.53 | 135508.74 | 11252.21 | 9.056% | Watch
Friedrichshain Loft | Structure | Max Bögl | 203735.54 | 195214.39 | -8521.15 | -4.182% | On Track
Prenzlauer Berg Retail | Finishing | Bilfinger SE | 296824.16 | 262043.34 | -34780.82 | -11.72% | On Track
Kreuzberg Residential | Structure | Züblin AG | 228039.86 | 245179.54 | 17139.68 | 7.516% | Watch
Kreuzberg Residential | Mep | Goldbeck GmbH | 263606.93 | 258399.15 | -5207.78 | -1.976% | On Track
Charlottenburg Hotel | Finishing | Bilfinger SE | 234773.98 | 227498.98 | -7275 | -3.099% | On Track
Mitte Office Tower | Mep | Hochtief AG | 523414.42 | 479256.46 | -44157.96 | -8.437% | On Track
Spandau Logistics Hub | Structure | Ed. Züblin | 360540.88 | 423843.31 | 63302.43 | 17.56% | Over Budget
Wedding School Extension | Mep | Goldbeck GmbH | 418135.98 | 366252.99 | -51882.99 | -12.41% | On Track
Lichtenberg Warehouse | Finishing | Porr GmbH | 356054.64 | 334033.08 | -22021.56 | -6.185% | On Track
Neukölln Mixed-Use | Foundation | STRABAG SE | 293919.34 | 337752.87 | 43833.53 | 14.91% | Over Budget
Charlottenburg Hotel | Structure | Goldbeck GmbH | 208894.01 | 204756.48 | -4137.53 | -1.981% | On Track
Prenzlauer Berg Retail | Mep | Goldbeck GmbH | 351410.57 | 309300.87 | -42109.7 | -11.98% | On Track
Mitte Office Tower | Finishing | Bauer GmbH | 364071.6 | 372724.66 | 8653.06 | 2.377% | Watch
Lichtenberg Warehouse | Foundation | Bauer GmbH | 204968.36 | 191816.73 | -13151.63 | -6.416% | On Track
Kreuzberg Residential | Finishing | Züblin AG | 324395.44 | 287682.2 | -36713.24 | -11.32% | On Track
Spandau Logistics Hub | Mep | Bilfinger SE | 426662.14 | 492076.94 | 65414.8 | 15.33% | Over Budget
Prenzlauer Berg Retail | Structure | STRABAG SE | 439784.02 | 490911.25 | 51127.23 | 11.63% | Over Budget
Lichtenberg Warehouse | Mep | Bilfinger SE | 221923.51 | 196026.61 | -25896.9 | -11.67% | On Track
Steglitz Medical Centre | Mep | Hochtief AG | 426227.21 | 372463.94 | -53763.27 | -12.61% | On Track
Steglitz Medical Centre | Finishing | Implenia DE | 379955.07 | 341871.63 | -38083.44 | -10.02% | On Track
Charlottenburg Hotel | Mep | Implenia DE | 435949.93 | 471617.57 | 35667.64 | 8.182% | Watch
Prenzlauer Berg Retail | Foundation | Max Bögl | 464412.86 | 432372.28 | -32040.58 | -6.899% | On Track
Mitte Office Tower | Structure | Max Bögl | 268620.96 | 263774.49 | -4846.47 | -1.804% | On Track
Spandau Logistics Hub | Foundation | Bauer GmbH | 341899.67 | 400150.66 | 58250.99 | 17.04% | Over Budget
Kreuzberg Residential | Foundation | Porr GmbH | 166823.72 | 159125.39 | -7698.33 | -4.615% | On Track
Spandau Logistics Hub | Finishing | Implenia DE | 210579.05 | 184619.22 | -25959.83 | -12.33% | On Track
Wedding School Extension | Finishing | Bilfinger SE | 373161.68 | 422337.78 | 49176.1 | 13.18% | Over Budget
Steglitz Medical Centre | Foundation | Porr GmbH | 460231.54 | 499697.01 | 39465.47 | 8.575% | Watch
Friedrichshain Loft | Foundation | STRABAG SE | 518392.93 | 506403.46 | -11989.47 | -2.313% | On Track
Wedding School Extension | Structure | Bauer GmbH | 171964.16 | 184312.34 | 12348.18 | 7.181% | Watch
Lichtenberg Warehouse | Structure | Goldbeck GmbH | 170679.01 | 169665.07 | -1013.94 | -0.5941% | On Track
Steglitz Medical Centre | Structure | Ed. Züblin | 555000.91 | 507673.18 | -47327.73 | -8.528% | On Track
Friedrichshain Loft | Mep | Goldbeck GmbH | 483254.12 | 461916.84 | -21337.28 | -4.415% | On Track
Wedding School Extension | Foundation | STRABAG SE | 342291.01 | 366271.98 | 23980.97 | 7.006% | Watch
Neukölln Mixed-Use | Foundation | Max Bögl | 212509.83 | 238225.11 | 25715.28 | 12.1% | Over Budget
Friedrichshain Loft | Finishing | STRABAG SE | 315120.31 | 354172.44 | 39052.13 | 12.39% | Over Budget
Charlottenburg Hotel | Foundation | Porr GmbH | 191538.52 | 213184.24 | 21645.72 | 11.3% | Over Budget
Neukölln Mixed-Use | Structure | Max Bögl | 436635.86 | 391701.82 | -44934.04 | -10.29% | On Track
Neukölln Mixed-Use | Finishing | Ed. Züblin | 303787.08 | 273891.54 | -29895.54 | -9.841% | On Track
Total Budget | 13074447.34
Total Actual | 13025726.58
Total Variance | -48720.76
Avg Variance % | -0.00762%
# Over Budget | 9
# On Track | 24

## 6_Dashboard
Berlin Construction Cost Tracker
Project Budget & Variance Analysis ¦ Berlin, Germany ¦ 2023-2024
TOTAL BUDGET |  | TOTAL ACTUAL |  | TOTAL VARIANCE |  | AVG VARIANCE % | # OVER BUDGET | # ON TRACK
13074447.34 |  | 13025726.58 |  | -48720.76 |  | -7.6203e-05 | 9 | 24
COST BY PHASE
Phase | Budget | Actual | Variance | Variance % | Status
Foundation | 3321244.31 | 3480508.47 | 159264.16 | 4.795% | Watch
Structure | 3043895.21 | 3077031.87 | 33136.66 | 1.089% | Watch
Finishing | 3158723.01 | 3060874.87 | -97848.14 | -3.098% | On Track
Mep | 3550584.81 | 3407311.37 | -143273.44 | -4.035% | On Track
Total | 13074447.34 | 13025726.58 | -48720.76 | -0.3726%
PROJECT VARIANCE SNAPSHOT
Project Name | Total Budget | Total Actual | Variance | Variance % | Rag Status
Mitte Office Tower | 1280363.51 | 1251264.35 | -29099.16 | -2.273% | On Track
Kreuzberg Residential | 982865.95 | 950386.28 | -32479.67 | -3.305% | On Track
Prenzlauer Berg Retail | 1552431.61 | 1494627.74 | -57803.87 | -3.723% | On Track
Charlottenburg Hotel | 1071156.44 | 1117057.27 | 45900.83 | 4.285% | Watch
Neukölln Mixed-Use | 1246852.11 | 1241571.34 | -5280.77 | -0.4235% | On Track
Spandau Logistics Hub | 1339681.74 | 1500690.13 | 161008.39 | 12.02% | Over Budget
Friedrichshain Loft | 1520502.9 | 1517707.13 | -2795.77 | -0.1839% | On Track
Wedding School Extension | 1305552.83 | 1339175.09 | 33622.26 | 2.575% | Watch
Steglitz Medical Centre | 1821414.73 | 1721705.76 | -99708.97 | -5.474% | On Track
Lichtenberg Warehouse | 953625.52 | 891541.49 | -62084.03 | -6.51% | On Track
Note: | Red = over 10% over budget
Yellow = 0-10% over
Green = on or under budget